## Effort Tracking
Issues | Summary of tasks | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors
1 | Create landing page | 30 | 40 | 0 | Richard Masuda | Richard Masuda
2 | Sign up page | 30 | 30 | 0 | Jiaxing Feng | Jiaxing Feng
3 | Log in page | 30 | 30 | 0 | Jiaxing Feng | Jiaxing Feng
4 | Profile page | 30 | 30 | 0 | Nalani Klopfenstein | Nalani Klopfenstein
5 | Create HomePost component | 30 | 30 | 0 | Andrew Bushong | Andrew Bushong
6 | Create user search page HTML | 15 | 10 | 0 | Jenebryan Mercado | Jenebryan Mercado
7 | Create search bar with filters | 45 | 20 | 0 | Jenebryan Mercado | Jenebryan Mercado
8 | Add user search page to navbar | 30 | 30 | 0 | Jenebryan Mercado | Jenebryan Mercado
9 | Draft results section | 15 | 10 | 0 | Jenebryan Mercado | Jenebryan Mercado
10 | Update project home page | 30 | 30 | 0 | Nalani Klopfenstein | Nalani Klopfenstein
11 | Implement HomePost on home page | 40 | 40 | 0 | Andrew Bushong | Andrew Bushong
12 | Admin page | 45 | 40 | 15 | Jiaxing Feng | Jiaxing Feng
13 | Sign out page | 30 | 30 | 5 | Jiaxing Feng | Jiaxing Feng
14 | Change password page | 30 | 45 | 10 | Jiaxing Feng | Jiaxing Feng
15 | Register page writes accounts to DB | 45 | 60 | 10 | Jenebryan Mercado | Jenebryan Mercado
16 | User search page pulls from database | 45 | 60 | 10 | Richard Masuda | Richard Masuda
17 | Create database structure | 60 | 75 | 15 | Jenebryan Mercado | Jenebryan Mercado
18 | Redirect logged-in users to home page | 15 | 15 | 5 | Richard Masuda | Richard Masuda
19 | Create edit profile page | 30 | 45 | 10 | Nalani Klopfenstein | Nalani Klopfenstein
20 | Implement posts from database to home page | 60 | 75 | 15 | Andrew Bushong | Andrew Bushong
21 | Create games page | 45 | 45 | 10 | Andrew Bushong | Andrew Bushong
23 | Create DB setup guide | 30 | 10 | 30 | Team | Team
24 | Troubleshoot issue-17 branch | 30 | 40 | 20 | Team | Team
25 | Create Playwright tests | 30 | 30 | 15 | Andrew Bushong | Andrew Bushong
26 | Update project home page (IO) | 30 | 30 | 5 | Nalani Klopfenstein | Nalani Klopfenstein
27 | Fix display issues | 30 | 40 | 15 | Jiaxing Feng | Jiaxing Feng
28 | Implements on admin page | 120 | 300 | 80 | Jiaxing Feng | Jiaxing Feng
29 | Implement create post page | 45 | 90 | 10 | Andrew Bushong | Andrew Bushong
30 | Create & implement “Request Event” tab/page | 45 | 60 | 10 | Richard Masuda | Richard Masuda
31 | View profile (Search tab) | 30 | 46 | 10 | Jenebryan Mercado | Jenebryan Mercado
33 | Implement admin-only access control | 60 | 60 | 10 | Jiaxing Feng | Jiaxing Feng
34 | Admin create event | 30 | 60 | 10 | Jiaxing Feng | Jiaxing Feng
36 | Implement posts to DB | 45 | 120 | 10 | Andrew Bushong | Andrew Bushong
37 | Edit profile | 30 | 42 | 10 | Jenebryan Mercado | Jenebryan Mercado
38 | Dropdown menu for edit games/interests | 10 | 16 | 5 | Jenebryan Mercado | Jenebryan Mercado
39 | Character limit in edit profile | 10 | 10 | 5 | Jenebryan Mercado | Jenebryan Mercado
40 | Fix change password bug | 20 | 30 | 10 | Richard Masuda | Richard Masuda
41 | Admin view event requests | 45 | 60 | 10 | Richard Masuda | Richard Masuda
42 | User search filters read from DB | 40 | 78 | 10 | Jenebryan Mercado | Jenebryan Mercado
43 | Implement filter functionality on UserSearch page | 30 | 63 | 10 | Jenebryan Mercado | Jenebryan Mercado
44 | Allow users to edit profile picture | 15 | 61 | 10 | Jenebryan Mercado | Jenebryan Mercado
45 | Games page filters posts | 60 | 120 | 10 | Andrew Bushong | Andrew Bushong
46 | Implement followers / following feature | 120 | 95 | 15 | Jenebryan Mercado | Jenebryan Mercado

## Sheet2
Team Member | Software Development Experience (months) | How is coding effort tracked? | How is non-coding effort tracked?
Jenebryan Mercado | 4 | Best guess | Best guess
Jiaxing Feng | 4 | Best guess | Best guess
Andrew Bushong | 4 | Best guess | Best guess
Nalani Klopfenstein | 4 | Best guess | Best guess
Richard Masuda | 4 | Best guess | Best guess